## FORECAST Planned Hours
RID | Personnel Number | Resource Name | Project Role | 2021-08-09 | 2021-08-16 | 2021-08-23 | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27
1 | 50000289 | Michael VanZuiden | Program/Project Manager | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 8 | 20 | 20 | 20 | 16 | 16
24 | 50000989 | Jason Garcia | Project Manager | [6 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
26 | 50000533 | Sabarinathan Lakshmanan | Offshore Mgr | 2021-09-06: 5; 2021-09-13: 5; 2021-09-20: 5; 2021-09-27: 5
2 | 50000415 | Umashankar Poojar | PM offshore | [6 empty] | 20 | 20 | 45 | 36 | 27 | 36 | 9 | 36 | 45 | 45 | 45 | 45 | 45 | 45 | 45
3 | 50000171 | Hector Koong | Architect | 2021-08-09: 40; 2021-08-16: 40; 2021-08-23: 40; 2021-08-30: 40; 2021-09-06: 40; 2021-09-13: 40
27 | 50002416_arch | Vipul Singh_arch | Architect | [6 empty] | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 36 | 40 | 40 | 40 | 40 | 40 | 36 | 40
18 | 50002416 | Vipul Singh | CRM Functional | 2021-08-09: 40; 2021-08-16: 40; 2021-08-23: 40; 2021-08-30: 40; 2021-09-06: 40; 2021-09-13: 40; 2021-09-20: 40; 2021-09-27: 40
6 | 50000229 | Naga Sai Adithya Tadakamalla | SAP Functional Lead | [6 empty] | 10 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 24 | 40 | 40 | 40 | 32 | 32
4 | 50001202 | Mansoob Khan | Functional - ISU Billing | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 24 | 40 | 40 | 0 | 0
5 | 50000045 | Mallikarjuna Kanala | FICA Functional | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 0 | 0 | 40
7 | 50000636 | Satya Reddy | Commerce Architect | 40 | 40 | 40 | 40 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
8 | 50000207 | Jerry Hsu | Commerce Frontend | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20
9 | 50000551 | Manjunatha Kashirudraiah | Commerce Frontend |  |  |  |  | 45 | 45 | 45 | 27 | 45 | 36 | 27 | 45 | 36 | 27 | 45 | 45 | 27 | 45 | 45 | 45 | 45
10 | 50002452 | Sandeep Deepak | Commerce Backend |  |  |  |  | 45 | 45 | 45 | 20 | 17.5 | 17.5 | 30 | 45 | 27 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 27
11 | 50000377 | Praveen Hamilpure | PWB | 2021-10-18: 23; 2021-10-25: 23; 2021-11-01: 18; 2021-11-08: 35; 2021-11-15: 35; 2021-11-22: 35; 2021-11-29: 35; 2021-12-06: 35; 2021-12-13: 35; 2021-12-20: 35; 2021-12-27: 35
13 | 50000493 | Ramesh Murthy | CPI Lead |  |  |  |  | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
25 | 50002850 | Maheen Latheef | CPI | [7 empty] | 45 | 45 | 36 | 45 | 45 | 18 | 45 | 45 | 45 | 45 | 45 | 45 | 36 | 36
15 | 50002879 | Krishna Kanth | Developer - ISU | 2021-09-06: 45; 2021-09-13: 45; 2021-09-20: 45; 2021-09-27: 45; 2021-10-04: 45; 2021-10-11: 36; 2021-10-18: 45; 2021-10-25: 45
16 | 50002852 | Silpa Yaragonda | Develolper - CRM |  |  |  |  | 45 | 45 | 45 | 45 | 45 | 18 | 27 | 45 | 27 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
17 | 50003051 | Mohammed Nabeel | Developer - ABAP | 2021-10-25: 45; 2021-11-01: 36; 2021-11-08: 45; 2021-11-15: 45; 2021-11-22: 45; 2021-11-29: 45; 2021-12-06: 45; 2021-12-13: 45; 2021-12-20: 45; 2021-12-27: 45
20 | 50000541 | Athul Sukumar | Testing - Commerce/CRM | 2021-11-08: 41; 2021-11-15: 41; 2021-11-22: 41; 2021-11-29: 41; 2021-12-06: 41; 2021-12-13: 41; 2021-12-20: 41; 2021-12-27: 22
21 | 50001510 | Vidhyasagar Ariharan | Testing - ISU Billing | 2021-11-22: 20; 2021-11-29: 20; 2021-12-06: 20; 2021-12-13: 20; 2021-12-20: 40; 2021-12-27: 35
22 | 50001512 | Sreehari Nair | Testing - Bill Print | 2021-11-22: 45; 2021-11-29: 45; 2021-12-06: 45; 2021-12-13: 45; 2021-12-20: 45; 2021-12-27: 45
28 | 50000423 | Ashwin Narayan | Developer - ISU | 2021-09-27: 45; 2021-10-04: 45; 2021-10-11: 45; 2021-10-18: 12; 2021-10-25: 12; 2021-11-01: 18; 2021-11-08: 9
32 | 50003052 | BIraja Samal | Developer - ABAP | 2021-10-25: 36; 2021-11-01: 36; 2021-11-08: 45; 2021-11-15: 45; 2021-11-22: 45; 2021-11-29: 45; 2021-12-06: 45; 2021-12-13: 45; 2021-12-20: 45; 2021-12-27: 45
31 | 50002606 | Darshan Patil | Developer - ABAP | 2021-11-22: 45; 2021-11-29: 45; 2021-12-06: 45; 2021-12-13: 45; 2021-12-20: 45; 2021-12-27: 45
30 | 50002587 | Shweta Sheelwant | Developer - ABAP | 2021-11-22: 45; 2021-11-29: 45; 2021-12-06: 45; 2021-12-13: 45; 2021-12-20: 45; 2021-12-27: 45
29 | 50000511 | Nimal Nazaruddin | Developer - ISU | 2021-10-25: 22.5; 2021-11-01: 9; 2021-11-08: 27; 2021-11-15: 27; 2021-11-22: 27; 2021-11-29: 27; 2021-12-06: 45; 2021-12-13: 45; 2021-12-20: 45; 2021-12-27: 45
37 | 50001931 | Subramanyam Borusu | Commerce Frontend | 2021-10-25: 22.5; 2021-11-01: 22.5; 2021-11-08: 22.5; 2021-11-15: 22.5; 2021-11-22: 22.5; 2021-11-29: 22.5; 2021-12-06: 22.5; 2021-12-13: 22.5; 2021-12-20: 22.5; 2021-12-27: 22.5
36 | 50000927 | Kalpesh Jain | CRM Technico/Functional | 2021-10-25: 20; 2021-11-01: 20; 2021-11-08: 20; 2021-11-15: 20; 2021-11-22: 20; 2021-11-29: 20; 2021-12-06: 20; 2021-12-13: 20; 2021-12-20: 20; 2021-12-27: 20
35 | 50000495 | Vishall Pradeep | Developer - BW | 2021-11-01: 22.5; 2021-11-08: 22.5; 2021-11-15: 22.5; 2021-11-22: 22.5; 2021-11-29: 22.5; 2021-12-06: 22.5; 2021-12-13: 22.5; 2021-12-20: 22.5; 2021-12-27: 18
34 | 50000389 | Prashant Kalkar | Developer - BW | 2021-11-01: 11; 2021-11-08: 22.5; 2021-11-15: 22.5; 2021-11-22: 9.5; 2021-11-29: 14; 2021-12-06: 18; 2021-12-13: 23; 2021-12-20: 22.5; 2021-12-27: 18
33 | 50000087 | Paul Tseng | Developer - BW | 2021-11-01: 20; 2021-11-08: 40; 2021-11-15: 0; 2021-11-22: 0; 2021-11-29: 32; 2021-12-06: 40; 2021-12-13: 20; 2021-12-20: 0; 2021-12-27: 0
38 | 50000073 | Chuan Wang | BW/Reporting Architect | 2021-11-08: 8; 2021-11-15: 8; 2021-11-22: 8; 2021-11-29: 8; 2021-12-06: 12; 2021-12-13: 12; 2021-12-20: 12; 2021-12-27: 0
39 | 50000279 | Ryan Esch | StreamServe/OT | 2021-11-15: 20; 2021-11-22: 20; 2021-11-29: 20; 2021-12-06: 20
12 | 50000900 | Srinivas Ellanki | StreamServe/OT | 2021-11-22: 10; 2021-11-29: 20; 2021-12-06: 20; 2021-12-13: 40; 2021-12-20: 40; 2021-12-27: 40
40 | 50003053 | Shadic Sherrif | PM offshore | 2021-11-15: 35; 2021-11-22: 35; 2021-11-29: 35; 2021-12-06: 35; 2021-12-13: 35; 2021-12-20: 35; 2021-12-27: 35
41 | 50003101 | Amardeep Kumar | CRM Developer
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15th Oct - India Public Holiday
Note on Q1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1st Nov - India Public Holiday 4th Nov - India Floating Holiday